## Product Backlog
Product Name: | Gjob (Gaganjeet's owesome bots)
Team ID: | GJ
Name: | Michael Yu
Initials: | MY
Student ID: | 1001317097
(Additional names for teams only)
Name: | Gaganjeet Singh
Initials: | GS
Student ID: | 1001070011
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 18
Sprint 1 Left | 18
Sprint 2 Left
Sprint 3 Left
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | As a... | I want to... | So that... | Notes
| 1 |  |  | PM | create robot parts | I can define robot models | No menu required here – run program, create a part | GS | 0
| 2 |  |  | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model | GS | 0
| 3 |  |  | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model | GS | 0
| 4 |  |  | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price | MY | 0
| 5 |  |  | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to disk and reload it next time the program runs
| 6 |  |  | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order | MY | 0
| 7 |  |  | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order | MY | 0
| 8 |  |  | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project |  | 0
| 9 |  |  | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order |  | 0
| 10 |  |  | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order |  | 0
| 11 |  |  | SA | create a bulk (2+) robot order for a Customer | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
| 12 |  |  | PM | hide robot parts | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models |  | 0
| 13 |  |  | PM | hide robot models | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders |  | 0
| 14 |  |  | SA | save a draft order and return to it later | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
| 15 |  |  | PM | add custom pictures to robot models | BC are more likely to buy my robots | (Probably can't address until Homework #6)
| 16 |  |  | BC | see a pie chart of a model's component costs | I can decide if I want a different model | (Probably can't address until Homework #6)
| 17 |  |  | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
| 18 |  |  | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)

## Sprint NN Backlog
Sprint # | 1 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-09-29
End on | 2016-10-06
Demo on
Total Tasks | 18
Day 1 Left | 18
Day 2 Left | 18
Day 3 Left | 18
Day 4 Left | 18
Day 5 Left | 18
Day 6 Left | 18
Day 7 Left | 18
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
MENU | GJ-Menudo | UML | Menu | MY | Robot Menu | Complete | Soup
UML01 | UML-Class | UML | Class | MY | UML Class Diagram | Complete | Classy not sassy
UML02 | UML-UseCase | UML | Use Case | MY | UML Use Case Diagram | Complete | Not to be confused with UPPERCASE DIAGRAMS
RP_C | RP-Class | Class | RobotPart | GS | RobotPart class | InProgress
RP_H | RP-Header | Header | RobotPart | GS | RobotPart Header | InProgress
CTRL | CL-Controller | Main | Controller | GS | Controller | InProgress
SA_C | SA-Class

## Sprint NN Backlog (2)
Sprint # | 1 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-10-07
End on | 2016-10-12
Demo on
Total Tasks | 18
Day 1 Left | 18
Day 2 Left | 18
Day 3 Left | 18
Day 4 Left | 18
Day 5 Left | 18
Day 6 Left | 18
Day 7 Left | 18
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
MENU | GJ-Menudo | UML | Menu | MY | Robot Menu | Complete
UML01 | UML-Class | UML | Class | MY | UML Class Diagram | Complete
UML02 | UML-UseCase | UML | Use Case | MY | UML Use Case Diagram | Complete
RP_C | RP-Class | Class | RobotPart | GS | RobotPart class | InProgress
RP_H | RP-Header | Header | RobotPart | GS | RobotPart Header | InProgress
CTRL | CL-Controller | Main | Controller | GS | Controller Main | InProgress
SA_C | SA-Class | Class | SalesAssoc | MY | SalesAssoc Class | Revisit | Dependency: Order Header
SA_H | SA-Header | Header | SalesAssoc | MY | SalesAssoc Header | Revisit
CUST_C | CUST_Class | Class | Customer | MY | Customer Class | Revisit | Dependency: Order Header
CUST_H | Cust_Header | Header | Customer | MY | Customer Header | Revisit
ORD_C | Order_Class | Class | Order | MY | Order Class | Revisit | Dependency: RobotModel
ORD_H | Order_Header | Header | Order | MY | Order Header | Revisit

## Sprint NN Backlog (3)
Sprint # | 1 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-10-13
End on | 2016-10-20
Demo on
Total Tasks | 18
Day 1 Left | 18
Day 2 Left | 18
Day 3 Left | 18
Day 4 Left | 18
Day 5 Left | 18
Day 6 Left | 18
Day 7 Left | 18
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
MENU | GJ-Menudo | UML | Menu | MY | Robot Menu | Complete
UML01 | UML-Class | UML | Class | MY | UML Class Diagram | Complete
UML02 | UML-UseCase | UML | Use Case | MY | UML Use Case Diagram | Complete
RP_C | RP-Class | Class | RobotPart | GS | RobotPart class | InProgress
RP_H | RP-Header | Header | RobotPart | GS | RobotPart Header | InProgress
CTRL | CL-Controller | Main | Controller | GS | Controller Main | InProgress
SA_C | SA-Class | Class | SalesAssoc | MY | SalesAssoc Class | Test
SA_H | SA-Header | Header | SalesAssoc | MY | SalesAssoc Header | Test
CUST_C | CUST_Class | Class | Customer | MY | Customer Class | Test
CUST_H | Cust_Header | Header | Customer | MY | Customer Header | Test
ORD_C | Order_Class | Class | Order | MY | Order Class | Revisit | Dependency: RobotModel
ORD_H | Order_Header | Header | Order | MY | Order Header | Revisit
SHOP_C | Shop_Class | Class | Shop | MY | Shop Class | Revisit | Dependency: Robot Model, Report
Shop_H | Shop_Header | Header | Shop | MY | Shop Header | Revisit